## Summary
Project Name | Template Project
Generated | 2026-06-13 21:42
Project Start | 2026-06-13
Project End | 2026-07-21
Total Tasks | 14
Overall Progress (%) | 42.01%
Completed Tasks | 2
In-Progress Tasks | 7
Not Started Tasks | 5
Critical Tasks | 0
Dependencies | 7
Resource Assignments | 0

## Task Schedule
ID | Task Name | Type | Start Date | End Date | Duration (Days) | Progress (%) | Indent Level | Critical | Auto Schedule | Deliverable | Assigned To | Notes
1 | Project Planning | Summary | 2026-06-13 | 2026-06-22 | 10 | 80% | 0 | No | Yes
2 | Requirements Analysis | Normal | 2026-06-13 | 2026-06-17 | 5 | 100% | 1 | No | Yes
3 | System Design | Normal | 2026-06-18 | 2026-06-22 | 5 | 60% | 1 | No | Yes
4 | Development | Summary | 2026-06-23 | 2026-07-07 | 15 | 41.48% | 0 | No | Yes
5 | Frontend Implementation | Summary | 2026-06-23 | 2026-07-04 | 12 | 60% | 1 | No | Yes
6 | UI Design | Normal | 2026-06-23 | 2026-06-26 | 4 | 100% | 2 | No | Yes
7 | UI Development | Normal | 2026-06-27 | 2026-07-04 | 8 | 40% | 2 | No | Yes
8 | Backend Implementation | Summary | 2026-06-23 | 2026-07-07 | 15 | 26.67% | 1 | No | Yes
9 | API Design | Normal | 2026-06-23 | 2026-06-27 | 5 | 80% | 2 | No | Yes
10 | API Implementation | Summary | 2026-06-28 | 2026-07-07 | 10 | 0% | 2 | No | Yes
11 | Authentication Module | Normal | 2026-06-28 | 2026-07-01 | 4 | 0% | 3 | No | Yes
12 | Data Access Layer | Normal | 2026-07-02 | 2026-07-07 | 6 | 0% | 3 | No | Yes
13 | Integration & Testing | Normal | 2026-07-13 | 2026-07-20 | 8 | 0% | 0 | No | Yes
14 | Release | Milestone | 2026-07-21 | 2026-07-21 | 5 | 0% | 0 | No | Yes

## Resource Allocation
Task ID | Task Name | Resource | Allocation (%)

## Dependencies
Predecessor ID | Predecessor | Successor ID | Successor | Type | Lag (Days)
2 | Requirements Analysis | 3 | System Design | FS | 0
1 | Project Planning | 4 | Development | FS | 0
6 | UI Design | 7 | UI Development | FS | 0
9 | API Design | 10 | API Implementation | FS | 0
11 | Authentication Module | 12 | Data Access Layer | FS | 0
4 | Development | 13 | Integration & Testing | FS | 0
13 | Integration & Testing | 14 | Release | FS | 0