## Task Schedule
ID | Task Name | Type | Start Date | End Date | Duration (Days) | Progress (%) | Assigned To | Deliverable | Task Notes
1 | Project Kickoff | Summary | 2026-01-06 03:00 | 2026-01-13 03:00 | 5 | 35% | PM Team | Project charter | Top-level summary task (dates/duration roll up from subtasks)
2 | Requirements gathering | Normal | 2026-01-06 03:00 | 2026-01-12 03:00 | 5 | 100% | Analyst | Requirements document
3 | Design review | Milestone | 2026-01-13 03:00 | 2026-01-13 03:00 | 0 | 0% |  |  | Zero-duration milestone
4 | Development Phase | Summary | 2026-01-14 03:00 | 2026-02-17 03:00 | 25 | 25% | Dev Team
5 | Backend API | Normal | 2026-01-14 03:00 | 2026-01-26 03:00 | 9 | 40% | Backend Dev | REST API v1
6 | Frontend UI | Normal | 2026-01-27 03:00 | 2026-02-10 03:00 | 11 | 20% | Frontend Dev | Web UI screens | Starts after Backend API (FS dependency)
7 | Integration testing | Normal | 2026-02-11 03:00 | 2026-02-17 03:00 | 5 | 0% | QA | Test report
8 | Project Complete | Milestone | 2026-02-18 03:00 | 2026-02-18 03:00 | 0 | 0% |  |  | Final milestone

## Dependencies
Predecessor ID | Predecessor | Successor ID | Successor | Type | Lag (Days)
2 | Requirements gathering | 3 | Design review | FS | 0
3 | Design review | 5 | Backend API | FS | 0
5 | Backend API | 6 | Frontend UI | FS | 0
6 | Frontend UI | 7 | Integration testing | FS | 0
7 | Integration testing | 8 | Project Complete | FS | 0